## How to use
90-day starter plan
Part of the IT/OT Monday Kit ¦ free to use and adapt
A week-by-week plan that needs no new budget and no new tools, only a few hours a week from a small joint group.
Phases: Align (people and decisions), Map (assets, access and obligations), Practise (recovery and response).
1. Assign an owner to each action on the Plan sheet and adjust weeks to fit your calendar.
2. Update Status each week. The Progress sheet counts what is done.
3. Effort is a rough estimate in hours for the owner. It is there to show the plan is affordable.
4. Actions that touch live OT systems (passwords, remote access, restores) go through your normal change control and need OT approval.
Shaded cells are for you to fill in.

## Plan
Plan
Days 1 to 90
Week | Phase | Action | Why it matters | Owner | Effort (hrs) | Status | Done date | Notes
1 | Align | Name an executive sponsor for IT and OT security risk. | Without one accountable name, every gap belongs to nobody. |  | 2 | Not started
1 | Align | Book a 60-minute kickoff with the IT security, OT or engineering, and safety leads. | Gets the three functions in one room from day one. |  | 2 | Not started
1 | Align | Run the 15-minute self-assessment together (01-Self-Assessment). | Agrees a shared starting point and next step. |  | 1 | Not started
2 | Align | Draft and agree the joint charter (04-IT-OT-Charter-Template). Set a meeting cadence. | Moves you from Level 1 to Level 2 on paper. |  | 4 | Not started
2 | Align | Pick one pilot site or production line for the next 90 days. | Small scope makes progress visible and keeps effort low. |  | 1 | Not started
3 | Map | Build a first OT asset list from what already exists: engineering drawings, purchase records, maintenance system, switch tables. | You cannot protect, patch or report on what you cannot list. |  | 8 | Not started
3 | Map | List every remote access path into the pilot site: vendor tools, VPNs, modems, cellular routers. | Remote access is the most common way into OT. |  | 4 | Not started
4 | Map | Fix quick wins under normal change control: change default passwords and disable unused remote access. | High risk reduction for almost no cost. |  | 6 | Not started
4 | Align | Sponsor check-in: share the asset list, remote access findings and quick wins. | Keeps the sponsor engaged and unblocks decisions. |  | 1 | Not started
5 | Map | List every mandate you face on the Mandates sheet of 02-Control-Crosswalk. | Turns 'everything is new' into one visible list. |  | 3 | Not started
6 | Map | Fill in the crosswalk for the pilot site: owner, status and evidence for each control. | Shows where one control already satisfies many mandates. |  | 8 | Not started
6 | Map | With the process safety team, flag the safety-critical and environmentally critical assets. | Focuses effort where consequences are highest. |  | 3 | Not started
7 | Practise | Confirm offline backups of controller logic and configurations exist. Test one restore. | Recovery depends on backups you have actually tested. |  | 6 | Not started
7 | Practise | Confirm manual operating procedures exist and are current for critical processes. | Manual operation is what kept plants running in real incidents. |  | 3 | Not started
8 | Map | Get the dates of the next planned outage and capex cycle. List security work that needs them. | Many OT fixes can only happen when the unit is down. |  | 2 | Not started
9 | Practise | Run the 60-minute tabletop exercise (05-Tabletop-Exercise). | Builds the joint team faster than any document. |  | 6 | Not started
10 | Practise | Update incident contacts, decision rights and regulatory reporting deadlines. | Reporting clocks start when the incident starts. |  | 3 | Not started
11 | Map | Write a one-page business case for the top three gaps (06-Business-Case-One-Pager). | Turns findings into funded work. |  | 4 | Not started
12 | Align | Report to the sponsor: re-run the self-assessment, crosswalk coverage, top gaps, next 90 days. | Shows progress in the sponsor's language. |  | 3 | Not started
13 | Align | Plan the next 90 days and choose the next site. | Keeps momentum and spreads the model. |  | 2 | Not started

## Progress
Progress
Calculated from the Plan sheet
Phase | Actions | Done | % done | Effort (hrs)
Align
Map
Practise
Total